## Instructions - READ FIRST
GENERAL INSTRUCTIONS
This worksheet will guide you through the process of defining the key milestones you expect your organization or participants to achieve, the timing of when you expect each milestone to be achieved, and the steps you will take to achieve each one. Please review the Example provided (last tab at the bottom on the right) before developing your own milestones.
You must "maximize" Excel and this window for this to work, and so you can see all of the required tabs. Excel should be "full-screen" - click the maximize button on the top right of Excel (PC) or top left (Mac) to do so.
Once the window is maximized, you should see tabs at the bottom of the screen similar to those below.
Step 1 - Complete your Milestones & Timeline: Regardless of how long you expect it to take to complete your project, implement your organizational priorities or interact with your program participants (6 weeks, 3 months, 1 year, 3 years), it is helpful to have key milestones along the way. This allows you to “check in” on interim achievements and make course corrections as necessary. Click on the STEP 1 tab below to enter your milestones and timeline.
Step 2 - Complete your Project Steps For each milestone you want the organization or those you serve to reach, there are activities, actions, and/or services that you must undertake, complete or provide in order to be successful. You need not articulate every step you plan to take, but simply summarize the critical elements that must occur to achieve each milestone. It's OK to combine several efforts for each milestone. Incorporate “If - then” logic: if we complete these activities, then the organization or participants will accomplish these milestones. Click on the STEP 2 tab below to enter the tasks associated with each milestone.
Step 3 - Copy your Worksheet into the Grant Application.
This is where it all comes together. Simply copy and paste the contents displayed on the Step 3 tab into the answer box in the third question on the Project Narrative page of the on-line grant application. You can also save this worksheet to a local or network drive on your computer by using the Office Button, Save (PC) prompts at the top left of the worksheet. Click on the STEP 3 tab below to review your statements, then copy and paste your final answer into the application.

## Step 1
INSTRUCTIONS: Consider the result you want your organization or those you serve to achieve. In order to get there, what are the 2 – 5 key progress points during the grant period that will tell you that you or they are on their way to achieving the result? Be sure to list changes or accomplishments that reflect behaviors or conditions that can easily be confirmed. When finished with this step, go to tab named Step 2. | List the date or timeframe when you expect the organization or participants to achieve each milestone.
Milestones | By When

## Step 2
INSTRUCTIONS: Consider the milestones your organization or participants need to achieve. What are the actions or activities you need to do in order to accomplish each milestone? List those activities in this column for each Milestone. It's OK to combine or summarize several activities together for each milestone. Just consider the "IF, THEN" logic. IF we complete these activities, THEN the organization or participants will accomplish the milestones. When finished with this step, go to tab named Step 3. | These are the Milestones you defined in Step 1. (edit below if necessary) | These are timelines you identified for each Milestone. (edit below if necessary)
Critical Steps | Milestones | By When
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0

## consolidation (hidden)
| THIS WORKSHEET IS NOT USER-EDITABLE | THIS WORKSHEET IS NOT USER-EDITABLE | THIS WORKSHEET IS NOT USER-EDITABLE | THIS WORKSHEET IS NOT USER-EDITABLE
| Critical Steps | Milestones | By When
1 | 0 | 0 | 0 | Milestone 1: 0 Milestone: 0 (0)
2 | 0 | 0 | 0
3 | 0 | 0 | 0
4 | 0 | 0 | 0
5 | 0 | 0 | 0

## Step 3
Your final Milestone statements are shown below. Click in the cell below, and copy and paste the text into the third question on the "Project Narrative" page of the on-line grant application (or re-type them as necessary).

## Example
Workforce Development Example Employee Skill Upgrade Program
Critical Steps | Milestones | By When (please enter specific months, e.g., June 2017, if at all possible)
Provide outreach to the community through posters, flyers, and presentations at Churches and other local community based organizations. | At least 30 at risk, underemployed adults will enroll into the program. | Month 1-2
Provide workshop and 1-1 sessions to assess participant skills, career interests and goals. | At least 25 participants create a plan of action to develop relevant skills and capacities to meet their employment goals. | Month 2-4
Facilitate training sessions in English literacy, computer literacy, interpersonal skill building, and GED preparation. | At least 18 participants demonstrate basic skills required to pursue a job in their field of interest. | Month 4-7
Provide resume writing, job interviewing, dress for success and negotiations skills training. | At least 15 participants accept a living wage job. | Month 8-9
Provide bi-weekly phone support to help participants resolve any issues that arise during their first 90 days of employment. | At least 12 participants maintain their job for at least 90 days. | Month 12

## Capacity Building Example (hidden)
Step # | Capacity Building Example Integrating Medicaid Billing
Step | Critical Steps | Milestones | By When
1 | Work with key program and intake staff to agree on common intake data. Configure new software and determine training curriculum/schedule. | New client management system is set up correctly so that all key staff can enter/view data in real time. | April '10
2 | Train staff on new software and revise internal procedures for both intake and program staff. | Key staff demonstrate their ability to enter, view and use data in real time. | July '10
3 | Begin using new intake and client management system for the first 30 days. | Intake staff confirm they can find, enter all view key client data during intake within 45-60 minutes. Program staff confirm they can find and use intake data to enroll participants into their program in 30 minutes or less. | August '10
4 | Use new intake and client management system for 90 more days. | Intake staff confirm they can find, enter all view key client data during intake within 30-45 minutes. Program staff confirm they can find and use intake data to enroll participants into their program in 20 minutes or less. | November '10
5 | Use new intake and client management system for 90 more days. | Intake staff confirm they can find, enter all view key client data during intake within 30 minutes. Program staff confirm they can find and use all relevant intake and program data to enroll participants into their program in 15 minutes or less. | March '10

## Systems Change (hidden)
Step # | Systems Change Creating Health Savings Accounts (HSAs)
Step | Critical Steps | Milestones | By When
1 | Complete and submit 15 publications and briefing books. | Top 10 media outlets pick up at least 2 stories and over 250 members of congress confirmed they reviewed the briefing materials prior to the health care conferences in DC. | 2011-06-01
2 | Organize and hold eight health care reform-related conferences on Capitol Hill for House and Senate staffers as well as members of the Washington, D.C. government relations and public policy communities. | At least 15 members of congress agree to take action to move the issue forward. | 2011-11-01
3 | Organize and hold small briefings with members of Congress and their staffs on specific health care reform issues identified as being timely and of special interest. Ensure that NCHF health care reform experts testified and submitted testimony to the appropriate Senate and House committees to educate policymakers as to the benefits of market-oriented health care reform. | Over 50 congressional leaders author “Dear Colleague” letters and insert brief analyses and backgrounders into the Congressional Record and a variety of Bills are designed to create HSAs. | 2012-04-01
4
5
6